## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
MILESTONE: TABLET ORDERING & PROUCREMENT
Meet with GM on how many tablets to aquire | must have correct qty |  |  | 0 | Peta/Deanna
Research tablet models best suited for rollout | research best specs and value |  |  | 0 | Peta
Genereate quotes and review costs | reach out to vendors |  |  | 1 | Peta
Order tablets | get tracking number |  |  | 0 | Peta
Take delievery of new tablets at both locations | Confirm merchandise are not defective |  |  | 10 | Gilly/Alex
Receieve and choose mockups of tablet branding | Make sure stakeholders approve |  |  | 1
Connect with marketing to update new menu | Make sure stakeholders approve |  |  | 7 | Carter
MILESTONE: TESTING TABLET OPERATIONS
Hire electrician to install tablets at north location | confirm layout is correct |  |  | 1
Hire electrician to install tablets at downtown location | confirm layout is correct |  |  | 1
Confirm tablets are powered and operational | Make sure tablets are working |  |  | 0
Sync new tablet system with existing POS | intergate both systems |  |  | 3
Test software is running smoothly | avoid any software issues |  |  | 1
MILESTONE: TRAINING STAFF
First party vendor train key staff on new software | must be first party to avoid confusion |  |  | 1 | Terrific tablets
Key staff train north location | need good collaboration |  |  | 2 | Seyou
Key staff train downtown location | need good collaboration |  |  | 2 | Seyou
Create a Tablet/POS Management Team | tablet management is essential |  |  | 1
Gather feedback from all staff | critical feedback is important |  |  | 1
make changes based on staff feedback | critical feedback is important |  |  | 3
MILESTONE: TEST LAUNCH DAY
initiate a test run at both locations with friends and family | need honest critique |  |  | 1 | Deanna
gather feedback from test run from both locations | use metrics |  |  | 1 | Seyou
implement changes based on feedback | must act on feedback |  |  | 2
MILESTONE: LAUNCH DAY
Hold meetings on both locations to make sure all staff are ready | staff training is crucial |  |  | 1 | Deanna,Gilly,Alex
Confirm all hardware and software are working properly | systems must work accordingly |  |  | 0
"Open the doors" | launch day |  |  | 0 | Peta
Gather essential feedback | hold surveys |  |  | 0

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Meet with GM on how many tablets to aquire |  | 0 | 0 | 1 | 2 | H
Research tablet models best suited for rollout |  | 1 | 0 | 1 | 2 | H
Genereate quotes and review costs |  | 2 | 1 | 2 | 4 | H
Order tablets |  | 0 | 0 | 1 | 2 | H
Take delievery of new tablets | recent shipment issues may affect delivery ETA | 10 | 7 | 8 | 10 | M
design mockups of tablet branding |  | 2 | 2 | 5 | 7 | H
Hire electrician to install tablets at north location |  | 1 | 1 | 2 | 3 | H
Hire electrician to install tablets at downtown location |  | 1 | 1 | 2 | 3 | H
Confirm tablets are powered and operational |  | 0 | 0 | 1 | 2 | M
Sync new tablet system with existing POS | software must be updated to 3.0 | 3 | 2 | 3 | 4 | L
Test software is running smoothly |  | 0 | 0 | 1 | 2 | M
initiate a test run at both locations with friends and family |  | 1 | 0 | 1 | 2 | H
gather feedback from test run from both locations |  | 1 | 1 | 1 | 2 | H
implement changes based on feedback | ETA to complete depends on feedback receieved | 2 | 3 | 4 | 6 | M
Hold meetings on both locations to make sure all staff are ready |  | 0 | 0 | 1 | 2 | H
Confirm all hardware and software are working properly |  | 0 | 0 | 1 | 2 | M
train all staff on tablets implementation | Seydou will lead to train key staff | 10 | 10 | 14 | 21 | H
Gather essential feedback | confirm feedback is authentic | 0 | 0 | 1 | 2 | M
design mock up of menu items and coupons | Carter's work time flucuates based on inspiration | 3 | 3 | 5 | 7 | M

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Strategies for new menu rollout | https://www.barandrestaurant.com/operations/strategies-new-menu-rollouts | 2023-02-03 | Good do's and donts and tips about adding tablets to your restaurant
Rollout a New POS to Your Restaurant Chain | https://www.speedlinesolutions.com/blog/rollout-a-new-pos-to-your-restaurant-chain | 2023-02-03 | Perspective from a business owner point of view

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
faster, more efficient experience | 98% order accuracy or higher | Can we confirm orders by both kitchen staff and customers are being processed correclty? | ensure waiters have properly trained customers on new tablet ordering process | FALSE
faster, more efficient experience | achieve ticket time of 8 min for appetizers and 12-15 min for entrees | Does the kitchen have enough personell to handle deman and complete orders on time | track order flow and process form start to end and identify any disruptions between | FALSE
faster, more efficient experience | checkout time less than 1 minute | What are positives from achieving checkout time of 1 minute or less? | make sure user interface at the checkout screen is easy to noavigate | FALSE
faster, more efficient experience | maintain less than 5% of tablets with issues | Are the tablet software and hardware working properly? | Have tablet vendor run diagnostics to make sure they are operating correctly | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
faster, more efficient experience | 98% order accuracy or higher | Can we confirm orders by both kitchen staff and customers are being processed correclty? | How easy is it to order food from the tablet | Multiple choice | Very easy | Easy | Neutral | Hard | Very hard
faster, more efficient experience | 98% order accuracy or higher | Can we confirm orders by both kitchen staff and customers are being processed correclty? | Was your order correclty recieved? | Yes/No | Yes | No
faster, more efficient experience | 98% order accuracy or higher | Can we confirm orders by both kitchen staff and customers are being processed correclty? | Were you satisfied with your ordering experience? If no, please explain | Yes/No | Yes | No, please explain
faster, more efficient experience | achieve ticket time of 8 min for appetizers and 12-15 min for entrees | Does the kitchen have enough personell to handle deman and complete orders on time | How long did it take to receieve your appetizer? | Multiple choice | 0-5 min | 6-10min | 11+ min
faster, more efficient experience | achieve ticket time of 8 min for appetizers and 12-15 min for entrees | Does the kitchen have enough personell to handle deman and complete orders on time | How long did it take to receieve your entree? | Multiple choice | 0-10 min | 11-20min | 21-30min | 31-40min | 50+ min
faster, more efficient experience | checkout time less than 1 minute | What are positives from achieving checkout time of 1 minute or less? | Did you have diffucitly checking out? | Yes/No | Yes | No
faster, more efficient experience | checkout time less than 1 minute | What are positives from achieving checkout time of 1 minute or less? | How difficult was it to check out? | Multiple choice | Very easy | Easy | Neutral | Hard | Very hard
faster, more efficient experience | maintain less than 5% of tablets with issues | Are the tablet software and hardware working properly? | Did the tablet work properly? | Yes/No | Yes | No
faster, more efficient experience | maintain less than 5% of tablets with issues | Are the tablet software and hardware working properly? | If you can change anything about the tablet interface what would it be? | Open-ended | Please explain: